## Sheet1
No | Package | Type | Project | ComponentName | TaskID | MT_Number | ItemName | MT_Needed | Type of Comment | BB | Baseline | Database | ItemRevision | Owner Contact | Task Jira | TaskGroup | Tester | PeerReviewer | Status Review | ELOC Assigned | ELOC Recheck With Tool | LOC Complete | Estimation base TOOL | Actual hour | Status | Release Date | Planned Start | Planned End | Start | End | Status Result | C0 | C1 | MCDC | OPL/Defect | Reason For code coverage | Reason for Fail Testcase | Remark
38 | 20200518 | PSW | GEELY_FS11_ESP9.3HD_BSS05_SP05 | Geely_ESP93_Carbon_Int\MainstreamF30\rb\as\geely\CpiwAPB\app\dsm\RBHMI\src\RBHMI_Synchronisation_F30.C | 1473225 | - | RBHMI_Synchronisation_F30.c | - | Auto | BB98153 & BB97958 & BB80790 & BB80795 | BSS05_SP05 | Geely_ESP93_Carbon_Int | - | MIAO Huafeng (CC-AS/EVA-SW32-CN) |  | - | phuong.nguyen-thanh |  |  | 86 | 86 | 86 | 1.52 | 0.5 | Ready for PLC | 2020-05-27 | 2020-05-18 | 2020-05-27 | 2020-05-19 | 2020-05-19 | OK | 100% | 100% | 100% | None | - | - | -
57 | 20200519 | PSW | FAW_TypeC2_BSL33_Security | FAW_MainPath_V2.0_Int\MainstreamF30\rba\Bldr\config\ApplicationLayer\rba_BldrCmp\src | 1474054 | - | rba_BldrCmp_Cfg_CheckMem.c | - | Manual | BB99856, BB99857 | None | FAW_MainPath_V2.0_Int | - | Thangamani Shanmugam (RBEI/EBB7) |  | - | phuong.nguyen-thanh |  |  | 145 | 355 | 355 | 6.31 | 4 | Ready for PLC | 2020-05-26 | 2020-05-19 | 2020-05-26 | 2020-05-22 | 2020-05-25 | NG | 100% | 91% | 43% | OPL | - Can't cover False case of if (retValue == E_OK) at line #87 because it's always true - Can't cover if ((RBFS_uC == RBFS_uC_RenesasD3) && (returnValue == E_OK)) case (T&&F) because returnValue is always equal E_OK - Can't cover ful MCDCs at line #298, line #314, line #330, line #346 beacause all of them are macros | - | Actual LOC: 355. Owner confirm it's not impact
68 | 20200520 | PSW | CNMS_179148_Carbon_ESP_BL07_SPRINT12 | CNMS_ESP_Carbon_Int\MainstreamF30\rb\as\cnms_core\app\net\scl\src\OBD\ComScl_Scl_OBD_Signal_Copy.c | 1329906 | - | ComScl_Scl_OBD_Signal_Copy.c | - | Manual | None | BL07_SPRINT12 | CNMS_ESP_Carbon_Int | - | YE Tianyu (CC-AS/ESW2-CN) |  | - | phuong.nguyen-thanh |  |  | 120 | 120 | 120 | 2.13 | 2 | Ready for review |  | 2020-05-20 | 2020-06-03 | 2020-05-20 | 2020-05-20 | OK | 100% | 100% | 100% | None | - | - | Please comment follow ASPICE Standard
70 | 20200520 | PSW | CNMS_179148_Carbon_ESP_BL07_SPRINT12 | CNMS_ESP_Carbon_Int\MainstreamF30\rb\as\cnms_core\app\net\scl\src\AxAyYrs\NET_SCL_Tx_AxExport.c | 1329906 | - | NET_SCL_Tx_AxExport.c | - | Manual | None | BL07_SPRINT12 | CNMS_ESP_Carbon_Int | - | YE Tianyu (CC-AS/ESW2-CN) |  | - | phuong.nguyen-thanh |  |  | 236 | 236 | 236 | 4.19 | 2 | Ready for review |  | 2020-05-20 | 2020-06-03 | 2020-05-20 | 2020-05-20 | OK | 100% | 100% | 100% | None | - | - | Please comment follow ASPICE Standard
71 | 20200520 | PSW | CNMS_179148_Carbon_ESP_BL07_SPRINT12 | CNMS_ESP_Carbon_Int\MainstreamF30\rb\as\cnms_core\app\net\scl\src\AxAyYrs\NET_SCL_Tx_AyExport.c | 1329906 | - | NET_SCL_Tx_AyExport.c | - | Manual | None | BL07_SPRINT12 | CNMS_ESP_Carbon_Int | - | YE Tianyu (CC-AS/ESW2-CN) |  | - | phuong.nguyen-thanh |  |  | 236 | 236 | 236 | 4.19 | 2 | Ready for review |  | 2020-05-20 | 2020-06-03 | 2020-05-20 | 2020-05-20 | OK | 100% | 100% | 100% | None | - | - | Please comment follow ASPICE Standard
108 | 20200522 | PSW | SGMW CN202SR India RC2 CPi 242816 BB81722 | SGMW_ESP93_Mainstream_RBVH_Int\MainstreamF30\rb\as\sgmw\CN210S\dcompr\src\RBFSWBootInterface_SGMW.c | 1481841 | - | RBFSWBootInterface_SGMW.c | - | Auto | BB81722 | None | SGMW_ESP93_Mainstream_RBVH_Int | - | To Trong Khoa (RBVH/EAS11) |  | - | phuong.nguyen-thanh |  |  | 25 | 25 | 25 | 0.44 | 0.1 | Ready for PLC | 2020-05-27 | 2020-05-22 | 2020-05-28 | 2020-05-26 | 2020-05-26 | OK | - | - | - | None | - | - | No function to test
109 | 20200522 | PSW | SGMW CN202SR India RC2 CPi 242816 BB81722 | SGMW_ESP93_Mainstream_RBVH_Int\MainstreamF30\rb\as\sgmw\CN210S\dsmpr\src\RBPduHandler_Callouts.c | 1481841 | - | RBPduHandler_Callouts.c | - | Auto | BB81722 | None | SGMW_ESP93_Mainstream_RBVH_Int | - | To Trong Khoa (RBVH/EAS11) |  | - | phuong.nguyen-thanh |  |  | 220 | 220 | 220 | 3.91 | 2 | Ready for PLC | 2020-05-27 | 2020-05-22 | 2020-05-28 | 2020-05-26 | 2020-05-26 | OK | 100% | 100% | 100% | None | - | - | -
110 | 20200522 | PSW | SGMW CN202SR India RC2 CPi 242816 BB81722 | SGMW_ESP93_Mainstream_RBVH_Int\MainstreamF30\rb\as\sgmw\CN210S\hswpr\tst\hswsim\src\TestEnvironment_NvM_CNMS_EV712048.c | 1481841 | - | TestEnvironment_NvM_CNMS_EV712048.c | - | Auto | BB81722 | None | SGMW_ESP93_Mainstream_RBVH_Int | - | To Trong Khoa (RBVH/EAS11) |  | - | phuong.nguyen-thanh |  |  | 7 | 7 | 7 | 0.12 | 0.1 | Ready for PLC | 2020-05-27 | 2020-05-22 | 2020-05-28 | 2020-05-26 | 2020-05-26 | OK | 100% | 100% | 100% | None | - | - | -
111 | 20200522 | PSW | SGMW CN202SR India RC2 CPi 242816 BB81722 | SGMW_ESP93_Mainstream_RBVH_Int\MainstreamF30\rb\as\sgmw\CN210S\hswpr\tst\hswsim\src\TestEnvironment_NvM_CNMS_EV712518.c | 1481841 | - | TestEnvironment_NvM_CNMS_EV712518.c | - | Auto | BB81722 | None | SGMW_ESP93_Mainstream_RBVH_Int | - | To Trong Khoa (RBVH/EAS11) |  | - | phuong.nguyen-thanh |  |  | 7 | 7 | 7 | 0.12 | 0.1 | Ready for PLC | 2020-05-27 | 2020-05-22 | 2020-05-28 | 2020-05-26 | 2020-05-26 | OK | 100% | 100% | 100% | None | - | - | -
112 | 20200522 | PSW | SGMW CN202SR India RC2 CPi 242816 BB81722 | SGMW_ESP93_Mainstream_RBVH_Int\MainstreamF30\rb\as\sgmw\CN210S\hswpr\tst\hswsim\src\TestEnvironment_NvM_CNMS_EV711009.c | 1481841 | - | TestEnvironment_NvM_CNMS_EV711009.c | - | Auto | BB81722 | None | SGMW_ESP93_Mainstream_RBVH_Int | - | To Trong Khoa (RBVH/EAS11) |  | - | phuong.nguyen-thanh |  |  | 7 | 7 | 7 | 0.12 | 0.1 | Ready for PLC | 2020-05-27 | 2020-05-22 | 2020-05-28 | 2020-05-26 | 2020-05-26 | OK | 100% | 100% | 100% | None | - | - | -
113 | 20200522 | PSW | SGMW CN202SR India RC2 CPi 242816 BB81722 | SGMW_ESP93_Mainstream_RBVH_Int\MainstreamF30\rb\as\sgmw\core\app\dcom\RBAPLCust\src\RBAPLCUST_DiagnosticSessionControl.c | 1481841 | - | RBAPLCUST_DiagnosticSessionControl.c | - | Auto | BB81722 | None | SGMW_ESP93_Mainstream_RBVH_Int | - | To Trong Khoa (RBVH/EAS11) |  | - | phuong.nguyen-thanh |  |  | 259 | 259 | 259 | 4.6 | 1 | Ready for PLC | 2020-05-27 | 2020-05-22 | 2020-05-28 | 2020-05-26 | 2020-05-26 | NG | 100% | 100% | 84% | OPL | - Can't cover full MCDCs at line #135 case (T&&F). Because it has already covered by if at line #129 - Can't cover full MCDCs at line #130 case (F&&?)(F&&?) because decision (RBAPLCUST_RollerBenchSessionState == RBAPLCUST_RollerBenchSessionState_NOT_ACTIVE) and (RBAPLCUST_RollerBenchSessionState != RBAPLCUST_RollerBenchSessionState_NOT_ACTIVE) are confict |  | -Owner confirm that's OK
115 | 20200522 | PSW | SGMW CN202SR India RC2 CPi 242816 BB81722 | SGMW_ESP93_Mainstream_RBVH_Int\MainstreamF30\rb\as\sgmw\core\app\dcom\RBAPLCust\src\RBAPLCUST_WDBI_NVMData.c | 1481841 | - | RBAPLCUST_WDBI_NVMData.c | - | Auto | BB81722 | None | SGMW_ESP93_Mainstream_RBVH_Int | - | To Trong Khoa (RBVH/EAS11) |  | - | phuong.nguyen-thanh |  |  | 115 | 115 | 115 | 2.04 | 0.5 | Ready for PLC | 2020-05-27 | 2020-05-22 | 2020-05-28 | 2020-05-26 | 2020-05-26 | OK | 100% | 100% | 100% | None | - | - | -
136 | 20200525 | PSW | FAW_C100_IPB1.1_BSS01 | FAW_IPB1.1_Int\FAW_IPB\rb\as\fawIPB\core\app\dcom\RBAPLCust\src\common\RBAPLCUST_DcmGetStoreType.c | 1484917 | - | RBAPLCUST_DcmGetStoreType.c | - | Manual | BB82026 | BSS01 | FAW_IPB1.1_Int | - | ZHENG Fangfang (CC-AS/EVA-SW33-CN) |  | - | phuong.nguyen-thanh |  |  | 12 | 12 | 12 | 0.21 | 0.1 | Ready for review |  | 2020-05-25 | 2020-06-01 | 2020-05-27 | 2020-05-27 | OK | 100% | 100% | 100% | None | - | - | Comment LV1
147 | 20200525 | PSW | FAW_C100_IPB1.1_BSS01 | FAW_IPB1.1_Int\FAW_IPB\rb\as\fawIPB\core\app\dcom\RBAPLCust\src\iBooster\RBAPLCUST_RDBI_AnalogData.c | 1484917 |  | RBAPLCUST_RDBI_AnalogData.c | - | Manual | BB82026 | BSS01 | FAW_IPB1.1_Int | - | ZHENG Fangfang (CC-AS/EVA-SW33-CN) |  |  | phuong.nguyen-thanh |  |  | 77 | 77 | 77 | 1.36 | 1 | Ready for review |  | 2020-05-25 | 2020-06-01 | 2020-05-27 | 2020-05-27 | OK | 100% | 100% | 100% | None | - | - | Comment LV1
147 | 20200525 | PSW | FAW_C100_IPB1.1_BSS01 | FAW_IPB1.1_Int\FAW_IPB\rb\as\fawIPB\core\app\dcom\RBAPLCust\RBAPLCUST_RDBI_AnalogData.c | 1484917 |  | RBAPLCUST_RDBI_AnalogData.c | - | Manual | BB82026 | BSS01 | FAW_IPB1.1_Int | - | ZHENG Fangfang (CC-AS/EVA-SW33-CN) |  |  | phuong.nguyen-thanh |  |  | 77 | 77 | 77 | 1.36 | 1 | Ready for review |  | 2020-05-25 | 2020-06-01 | 2020-05-27 | 2020-05-27 | OK | 100% | 100% | 100% | None | - | - | Comment LV1
147 | 20200525 | PSW | FAW_C100_IPB1.1_BSS01 | FAW_IPB1.1_Int\FAW_IPB\rb\as\fawIPB\core\app\dcom\RBAPLCust\src\RBAPLCUST_RDBI_AnalogData.c | 1484917 |  | RBAPLCUST_RDBI_AnalogData.c | - | Manual | BB82026 | BSS01 | FAW_IPB1.1_Int | - | ZHENG Fangfang (CC-AS/EVA-SW33-CN) |  |  | phuong.nguyen-thanh |  |  | 77 | 77 | 77 | 1.36 | 1 | Ready for review |  | 2020-05-25 | 2020-06-01 | 2020-05-27 | 2020-05-27 | OK | 100% | 100% | 100% | None | - | - | Comment LV1
Note on F8: EXTERNAL Nguyen Trung Hieu (Ban Vien, RBVH/EPS45): Please comment follow ASPICE Standard